## Agile Gantt
Epic | Sprint (Week) | Task | Owner | Status | Definition of Done | Evidence Link
Architecture | 1 | Define system block diagram | You | Not Started | Diagram committed to docs/
Architecture | 1 | Define ROS node graph | You | Not Started | ros_graph.png committed
ROS Basics | 1 | Create ROS2 workspace | You | Not Started | ros2_ws builds cleanly
ROS Basics | 1 | Publish fake /cmd_vel | You | Not Started | Topic visible via ros2 topic echo
Simulation | 2 | Create URDF/Xacro | You | Not Started | Robot loads in RViz
Simulation | 2 | Add simulated LiDAR | You | Not Started | LaserScan visible
Navigation | 3 | Integrate Nav2 (sim) | You | Not Started | Go-to-pose succeeds
Navigation | 3 | Run SLAM Toolbox | You | Not Started | Map saved and reloads
Firmware | 4 | Flash OpenCat baseline | You | Not Started | Stock skills execute
Firmware | 4 | Document serial protocol | You | Not Started | protocol.md committed
Integration | 5 | ROS serial bridge node | You | Not Started | ROS -> OpenCat command works
Integration | 5 | Map /cmd_vel to gait | You | Not Started | Robot walks forward/turns
Autonomy | 6 | Nav2 on real robot | You | Not Started | Autonomous navigation demo
Behavior | 7 | Implement sleep/idle states | You | Not Started | FSM transitions logged
Behavior | 7 | Battery monitoring topic | You | Not Started | Battery % published