## Robotic Dog Gantt
Phase | Week Start | Week End | Task | Deliverable | Status (Not Started / In Progress / Done) | Evidence (link, video, screenshot) | Notes / Issues
Phase 0: Architecture | 1 | 1 | System block diagram | Architecture PDF
Phase 0: Architecture | 1 | 1 | ROS graph design | ROS graph sketch
Phase 1: ROS Basics | 1 | 2 | ROS nodes & topics | Working ROS workspace
Phase 1: ROS Basics | 1 | 2 | Fake odometry | RViz visualization
Phase 2: Simulation | 2 | 4 | URDF/Xacro | Sim robot model
Phase 2: Simulation | 2 | 4 | Nav2 + SLAM | Saved map + Nav2 demo
Phase 3: Hardware Bring-up | 3 | 5 | MCU motor control | Motors spin via UART
Phase 3: Hardware Bring-up | 3 | 5 | Encoders | Encoder feedback validated
Phase 4: Integration | 5 | 7 | Real odometry | Correct TF tree
Phase 4: Integration | 5 | 7 | LiDAR integration | Live scan in RViz
Phase 5: Navigation | 7 | 8 | Nav2 on real robot | Autonomous navigation demo
Phase 6: Personality | 8 | 10 | Battery monitoring | Battery topic published
Phase 6: Personality | 8 | 10 | Sleep / wake + voice | Wake word demo